## MEMORANDUM

## Date	:	January 30, 2001 (Revised 3/13/01)

To	:	Lewis and Clark College

Attention	:	Michael Sestric

Sent By	:	Will Dann

Project	:	Social Sciences Building

Job No.	:	0104

Re	:	Schematic Design Work Plan

Prior to first meeting:

Review Committee Meeting Notes

Review Draft Program

1.	Start-up									January 30, 2001

Meeting with Committee							11:30-1:30 Thayer 3

Process and Schedule

### Project Goals

### Master Plan Review and Site Conditions

Issue questionnaire

Preliminary Program

Tour of existing facilities

Products

Meeting Notes

Statement of Goals

Preliminary Program Analysis

2.	Detailed Program Interviews						week of February 5th

Meetings with Staff					Times and Locations to be determined

Social Science Administrative Spaces (with Department Heads and Administrative personnel)

Facilities/Grounds

### Other specific spaces as required

Products:

Meeting Notes

Organizational Concepts

3.	Program Summary / Organizational Concepts				February 15, 2001

### Meeting with Committee							11:30-1:30 Edmunds 9

Review of Statement of Goals

### Review Revised Program Analysis

Review Detailed Program Requirements

Program Relationship Concepts

Products:

Meeting Notes

Design Concept Diagrams

4.	Preliminary Design Concepts						February 27, 2001

### Meeting with Committee.							11:30-1:30 Stamm West

Alternative Building Concepts

Design Team Meetings (Structural, Landscape, Civil, MPE and CMGC)

Review Design Options

Products

Meeting Notes

Program Layout Diagrams

Site Design Concepts

5.	Site/Building Design Options						March 13, 2001

Meeting with Committee							11:30-1:30 Thayer 1&2

Program Layout options for selected Concept(s)

Program Area Comparisons

Select preferred Option

Products

Meeting Notes

Preliminary Schematic Design

Preliminary Building Code Review

6.	Develop Preferred Design							March 22, 2001

### Meeting With Committee							11:30-1:30 Stamm West

Present refined schematic Plans

Present Preliminary Building Elevations

Present Preliminary Site Plan

Present Updated Program Compliance

Meeting with Facilities Personnel

Present refined schematic Plans

Present preliminary Site Plan

Meeting with Building Department

Design Team Meeting (Structural, Landscape, Civil, MPE and CMGC)

Develop Engineering Concepts

Products

Meeting Notes

7.	Refine Schematic Design							April 10, 2001	Meeting With Committee							11:30-1:30, Edmonds  9

Present refined schematic Plans

Present Refined Building Elevations

Products

Meeting Notes

Cost Estimate Drawings

Outline Specification

Cost Estimate Review and Value Engineering

8.	Cost Reconciliation								May 1, 2001

Meeting With Committee							11:30-1:30, Stamm West

Present Preliminary Cost Estimate (HCC)

Present Alternates (as needed)

Products

Meeting Notes

Value Engineering Revisions (as needed)

9.	Final Schematic Design								May 22,  2001

Meeting With Committee							11:30-1:30, Thayer 1&2

Present Final Schematic Plans

Present Final Building Elevations

Present final Cost estimate (HCC)

Products

Meeting Notes

Design Development Work Plan

Overall Project Schedule

Design Development			6/1/01 – 9/20/01

Value Engineering			10/01/01 – 10/31/01

Contract Documents			12/01/01 – 4/30/02

Permit					5/1/02 – 9/30/02

Bid/Negotiation				3/1/03 – 5/30/03

Construction				6/1/03 – 7/30/04

Move-in					8/1/04 – 8/30/04